## Slide 1
WVL-N
END
OF
PROJECT
REPORT

## Slide 2
Table of Content
1. Executive Summary
2.. Introduction
3. Project Objectives
4. Key Achievements
5. Challenges and Lessons Learned
6. Impact Stories
7. Sustainability Measures
8. Conclusion
9. Appendices

## Slide 3
Executive Summary
The Women's Voice and Leadership Nigeria (WVL-N) project is managed by ActionAid Nigeria and implemented by Child Care and Adult Protection Initiative (CCAPI), Gender And Development Action (GADA), and Neighbourhood Care-Well Foundation (NCF) with support from 12 community-based organizations in Cross River State. The project is a five-year Global Affairs Canada development assistance with the goal to support the capacity and activities of local and women’s rights organizations and movements, seeking to empower women and girls, advance the protection of women and girls’ rights and achieve gender equality. The project which is in its final year has provided technical support to 15 Local Women’s Rights Organizations (LWROs) and Community Based Organizations(CBOs) across the 3
senatorial districts of Cross River State. The project covers three thematic areas such as Women Economic Empowerment, Women Political Participation, Leadership & Decision-making and Protecting Women and Girls from Gender Based Violence. A total sum of N310,345,279.99 (Three Hundred and Ten Million, Three Hundred and Forty-Five Thousand, Two Hundred and Seventy-Nine Naira, Ninety-Nine Kobo) only, has been spent by the funders from 2019 to date to implement the WVL-N project in Cross River State. The project has yielded laudable results from the past 5 years of its implementation in Cross River State. Based on our factsheet, we have an overall direct reach of 148,153 women and girls and indirect reach of 6, 350, 024 from the 12 LGAs in Cross River State which includes; Odukpani, Akpabuyo, Calabar Municipality and Calabar South. We also worked with 12 women Community Based Organizations in six Local Government Areas which includes Calabar South, Bakassi and Obudu.

## Slide 4
Introduction
The Women's Voice and Leadership Nigeria Project (WVL) in Cross River State has played a pivotal role in eempowering women through financial independence to reduce vulnerability, promoting women's political participation and protecting women and girls from gender-based violence. The expected outcomes from the project were: Improved management and sustainability of local women’s rights organizations in Nigeria; Enhanced delivery of programming and advocacy to advance gender equality by local women’s rights organizations in Nigeria; Increased effectiveness of sub-national, national, and regional women’s rights platforms, networks, and alliances to affect policy, legal and social change in Nigeria. The WVL project which began in 2019 was focused on Women Economic Justice and Empowerment ,Women political participation, leadership and decision making, and addressing Gender-Based Violence against women and girls. The ultimate outcome was Increased enjoyment of human rights by women and girls and the advancement of gender equality in Nigeria.

## Slide 5
Project Objectives
To empower Women through Financial Independence to Reduce Vulnerability.
To sustain Economic Empowerment.
To strengthen women owned businesses; by controlling taxation and exploitation of women owned businesses.
Build new partnerships and interact with relevant Community stakeholders to encourage better political participation & representation, support for women aspirants/candidates and increased women voter turnout during elections
Encourage women’s political participation, leadership and decision making
Mainstream young women in tertiary institutions into political activities and school politics
Strengthen women’s political participation to become influencers of policy affecting women in the society.
Work to protect women and girls from violence, create opportunities for economic independence and decision making

## Slide 6
Key Achievements
CCAPI’s skill-building opportunities successfully empowered 746 women directly and 1570 persons indirectly with no prior skill knowledge and transformed them into entrepreneurs, through various skill acquisition programs, financial literacy training, and economic empowerment initiatives. Currently, 103 out of 350 women who were empowered with start up items have been able to begin and sustain their businesses and 11 of them have replicated skills learnt to 172 other vulnerable women who now earn an average of 10-50 Thousand Naira per month which have improved their standard of living and led to increased financial independence and reduced vulnerability among the beneficiaries.

## Slide 7
Awareness campaigns to educate women in communities on financial literacy had an influence on policies on taxation around exploitation of small and medium sized businesses -through CCAPI’s efforts in collaboration with IRS, Ministry of commerce, FIDA and other state actors, 11 women within the metropolis can now channel their payment in a regulated and transparent way – it has been made known to women the communication and reporting channels of any form of tax related abuse or exploitation, this is as a result of the work and collaboration with the commissioner of commerce through the state government who through her engagement in the WVL project with CCAPI and other partners in the state was appointed the commissioner of commerce.

## Slide 8
CCAPI formed advocacy working groups and conducted consultative meetings to collaborate with women and understand their challenges, leading to effective problem-solving and sustainable solutions. Structures like 2 functional peer education and VLSA groups, women in maritime business trade who function independently.
Through the project, CCAPI has strengthened its visibility, gainful collaborations and partnerships – through the project, CCAPI has received over 4.7 million naira in grants from NEPC and the federal Ministry of Women Affairs, CCAPI was able to pay for a land at a discounted rate given by the Kasuk community where CCAPI’s office and skills centre is currently being built.

## Slide 9
Provided relief materials to 50 beneficiaries during COVID-19 pandemic through the Leading Girls Foundation, CCAPI donated improved variety rice seedlings and fertilisers to 9 cooperative groups who are farmers through her partnership with Ministry of Agriculture on the Cadre Harmonize Programme, donated 10kg parboiled rice to 30 households through NCF donated by Dangote foundation Initiative. The organization has also donated school materials to100 school students and provided scholarships to 20 others through the United Way Greater Nigeria etc.
Supported women in maritime business and trade, providing training on exportation, quality assurance, and business development, which has led to increased participation of women in the export market.

## Slide 10
The project fostered collaboration with government authorities, NGOs, and other stakeholders, leading to the successful implementation of various initiatives and the creation of a supportive network for women's economic empowerment. In view of this, CCAPI has collaborated with NEPC to facilitate the registration and participation of 25 women led cooperative groups in the maritime trade sector. Through the project, some of these cooperatives have been registered with NEPC, obtained tradenames, NAFDAC and received free export readiness trainings. Five of these groups are currently in the stage of testing their products in the local market and 2 have informally sold their products abroad to family and friends , which translates to increased profits and a better standard of living.

## Slide 11
Policy Influence and Legal Reforms: NCF Successfully influenced and contributed to the implementation of child protection policies and legal frameworks supporting women's and youths' rights.
Increased Public Awareness: NCF has Significantly raised public awareness about the rights and needs of children, women, and youths through targeted campaigns.
Strengthened Stakeholder Collaborations: we have built strong collaborations with governmental and non-governmental organizations, creating a unified front for advocacy efforts and policy change.

## Slide 12
Resource Mobilization: all our work has attracted increased funding and resources from international and local donors to support advocacy projects.
Stronger Collaboration with Authorities: NCF has strengthened partnerships with law enforcement and social services, leading to more efficient and effective handling of cases.
Improved Case Tracking and Monitoring: Enhanced tracking and monitoring systems to ensure that victims receive continuous and appropriate support.

## Slide 13
Enhanced Skills and Employability: Over 30 women and youths gained new skills through workshops and training programs.
Behavioral Change and Reduction in Harmful Practices: Achieved significant reductions in early marriage, gender-based violence, and other harmful practices.
Increased School Enrollment and Retention: Boosted school enrollment and retention rates, particularly for girls.
Improved Health Outcomes: Improved health and well-being of women and children through education on health practices, nutrition, and hygiene.
Development of Community Leaders: Trained and developed local leaders who now advocate for the rights and needs of their communities.
Creation of Supportive Environments: Established safe spaces for over 30 women and girls.
Mental Health and Well-being: Improved mental health and well-being among participants.

## Slide 14
Access to Resources and Services: Increased access to educational materials, health services, and vocational training within these safe spaces.
Empowerment and Informed Decision-Making: Empowered women and girls to make informed decisions and assert their rights.
Strengthened Social Networks: Fostered a sense of community and belonging among participants.
Effective Resolution of Cases: Successfully resolved over 2,000 cases of abuse, violence, and neglect.
Holistic Victim Support: we offered comprehensive support services, including legal aid, medical assistance, and psychological counseling. Empowered victims through education and support, enabling them to rebuild their lives and advocate for their rights.

## Slide 15
Challenges
Limited access to rural communities: Difficulty in reaching remote areas, making it hard to engage with target beneficiaries.
Cultural and social barriers: Resistance to change from traditional gender roles and stereotypes.
Limited financial resources: Insufficient funds to support project activities and sustain beneficiary engagement.
Gender-based violence: Prevalence of GBV cases among beneficiaries, requiring additional support and resources.
Stakeholder buy-in: Difficulty in engaging stakeholders, including government officials and community leaders.
COVID-19 pandemic: Restrictions on gatherings and movement, disrupting project activities and engagement.
Cash crunch before elections: Delayed funding disbursements, affecting project implementation and sustainability.

## Slide 16
Cultural stereotypes continue to limit women from reaching their fullest potential in politics, leadership and decision making in Cross River State
Apathy on the part of women who feel leadership are better exerted by men prevents them from aspiring for leadership positions
Financial constraints also hindered women from effectively competing with their male counterpart in politics
Women are still highly underrepresented in political offices limiting their influence in decision making process both at local and national levels
Biased media do not shine the spotlight on women which decreases their visibility and competence in leadership
Violence, intimidation and harassment of women who venture into politics continue to limit women
Young women in tertiary institutions have limited access to mentorship and role models which hinder their aspirations for those who want to venture into school politics.
During the 2023 elections, many women were apathetic to participating in the electoral process with the notion that their votes may not count, many women did not register for their Permanent Voters Card during the voter registration campaign.

## Slide 17
A culture of inclusivity is still at a low level in the state which is preventing dismantling systemic barriers to equality
Many women still struggle with balancing work life and family responsibilities which affects their career choices
Women seemed not to fully support other women aspirants in the 2023 election primaries in Cross River State which placed women aspirants on a low pedestal against their male counterparts
Limited Resources and Funding: Securing adequate funding and resources to sustain program activities and expand outreach.
Community Resistance and Cultural Barriers: Resistance to change and cultural norms that hindered acceptance of women and youth empowerment initiatives.
Legal and Institutional Constraints: Complex legal frameworks and bureaucratic hurdles affecting advocacy efforts and service delivery.
Socioeconomic Inequalities: Persistent poverty, lack of access to education, and economic opportunities among target populations.
Health and Well-being Challenges: High prevalence of health issues such as maternal mortality, malnutrition, and mental health challenges.

## Slide 18
Lessons Learned
Provided technical support for women to register for their continuous voter registration (CVR) increased voter turnout and exercise of their franchise during elections
Money politics limit the true representation of the right candidates during election primaries
Working with political parties to negotiate for women’s positions in the political space will provide women more chances prior to the primaries and elections
There is need for continuous voter education for women to increase their political participation and prevent apathy towards politics and leadership.
Gender sensitivity and issues are still new to majority which needs continuous awareness creation
Taking advantage of congress meetings ensures more women are involved in party politics

## Slide 19
The notion ‘Party is supreme’ significantly affects women’s leadership in party structures
Clear project planning and robust timeline management are essential for effective resource allocation and risk mitigation.
Continuous stakeholder engagement fosters ownership and sustainability of project outcomes.
Investing in women's leadership and empowerment through tailored training and mentorship programs enhances their influence and participation in decision-making.
Integrating health education with community outreach improves awareness and adoption of preventive healthcare practices, leading to better health outcomes.

## Slide 20
Impact Stories
‘TAX JUSTICE FOR WOMEN’
CCAPI worked with relevant stakeholders such as Cross River State Board of Internal Revenue Service, Ministry of Women Affairs, FIDA etc, to ensure the reduction of high taxation and avoid exploitation and harassment of women. This was done through advocacies and consistent sensitization on radio, and behavioral change materials. Trainings were conducted for market women in collaboration with CBOs like CWO in Yakurr LGA and Local Government Revenue office to sensitize the women on the right method of paying tax to avoid exploitation and harassment. Mrs Theresa and other women in Ijiman market now pay N100 per market day making a total of N500per week and N200 per month, hence the tax has been reduced from N600 per month to N200 per month, (I.e approximately 14%), and this has increased her profit for a better livelihood

## Slide 21
WOMEN’S EMPOWERMENT IN INTERNATIONAL TRADE
Women, especially in rural areas in Cross River State, live in poverty. This can be attributed to certain gender issues such as lack of women engagement in viable economic and leadership positions. However, a collaborative initiative between the government, non-profit organizations, and international trade partners sought to change this narrative by leveraging the potential of women in the agricultural sector. CCAPI keyed into the Cross River State(CRS) strategic objective to enhance agricultural export and promote small and medium scale businesses owned by women and youths. Partnership with government stakeholders like Nigeria Export Promotion Council(NEPC), Ministry of commerce etc., capacity building and registration of small Agric-food businesses for women cooperatives groups among communities in Cross River state were registered. Support provided for beneficiaries on the project ranges from; NAFDAC registration, trademarks acquisition, nurturing collaborations with the Nigerian Export Promotion Council (NEPC), facilitation trainings on Branding and Packaging suitable for export, linkage to loan facilities, among others. Their success went beyond their individual achievements; it uplifted the entire community, inspiring other women to pursue careers in maritime trade. The once male-dominated industry began to embrace gender diversity, recognizing the immense value these women brought.

## Slide 22
Political Empowerment: GADA's Contribution to Female Representation
Through the Women’s Voice and Leadership (WVL) Nigeria project, GADA sought for representation of women in governance through a high level advocacy meeting and interactive session with the Governor's wife, Dr. (Mrs.) Linda Ayade. The outcome of the meeting for women’s Political Participation produced 4 female Chairmen and 12 Vice Chairmen during the Benedict Ayade’s regime in the 2019 Local Government elections in CRS.

## Slide 23
BLESSING ALIM’s HISTORIC VICTORY
Through GADA’s support, Blessing Alims made history by winning the election and becoming the first female Student Union Government(SUG) President of the University of Calabar in 49 years, a testament to the power of support, breaking barriers and challenging traditional gender norms.

## Slide 24
Transforming Apathy into Leadership Excellence
Out of the 30 young women mentored through targeted capacity building trainings, 17 young women acquired the skills, knowledge, and self-assurance to step into the realm of politics and leadership, taking a stand to run for leadership positions in 3 educational institutions of Cross River State. Against all odds, they emerged victorious in their respective elections, bringing a much-needed wave of change and gender inclusivity to their campuses.

## Slide 25
Transforming Apathy into Leadership Excellence
Out of the 80 grassroots women of Akpabuyo and Odukpani trained on political education and capacity building, 18 women have stood strong, stepping down trainings to others, improved their communication skills and networked among others. The project has equipped these women with the skills and confidence to assume leadership roles, thereby fostering generational leadership development.
GADA's holistic approach to women's empowerment has also strengthened their voices and influence in decision-making processes.

## Slide 26
From Registration to Revolution: Women Shaping Tomorrow’s Future
The impact of GADA’s ‘Register and Vote Campaign’ was transformative. A total of 690 women, inspired and empowered by our campaign, successfully registered and exercised their right to vote in the 2023 elections including first time voters.

## Slide 27
Amplifying Women’s Rights with Unity:
A formidable coalition involving GADA, CCAPI, NCF and other women's rights organizations in the state, united to advocate for the domestication of the VAPP Act. The result of the collective efforts was remarkable and in December 2022, the Cross River State House of Assembly passed and enacted the VAPP Act into law.
Advocacy to former speaker of the CRS House of Assembly- Rt. Hon. Eteng Jonas-William

## Slide 28
The Orange Show: A dedicated and transformative radio talk show.
The WVL project produced a transformative radio talk show which emerged as a champion of gender equality, using the power of radio to inspire change. It became the first gender-exclusive radio show in Cross River State, Nigeria in advancing gender equality. The show continues to run till date in amplifying women's voices, fostering discussions on gender-related topics in achieving the Sustainable Development Goal 5 - Gender Equality.

## Slide 29
Empowering Women During a Pandemic
Training of 120 Women on Proper Saving Culture, and Skill Acquisition on Production of Soap and Hand Sanitizer with start-up grants of N5000 each boosted their economic resources during the Covid-19 pandemic. Two–third (80) of the trainees are now entrepreneurs, self-reliant and share their success stories as a motivation to other women in their communities.

## Slide 30
CHAMPIONING ADVOCATES FOR POLICY REFORMS
Neighbourhood Care-Well Foundation (NCF) advocacy efforts have encouraged greater participation of women in community governance and decision-making processes. By promoting gender equality and highlighting the importance of women's rights, the foundation has facilitated women's representation in key local committees and councils. These women leaders have become prominent advocates for policy reforms and legal protections, significantly impacting local policies to better support women's rights and ensure inclusive development. Through mentorship programs and showcasing success stories, NCF continues to inspire and empower the next generation of women leaders, fostering a supportive environment where women thrive and lead with confidence and determination.

## Slide 31
Sustainability Measures
Training local partners and communities to sustain project activities and ensure ownership.
Establishing community-led structures to continue advocacy and support for women's economic empowerment.
Collaborating with government, private sector, and civil society organizations to leverage resources and support.
Identifying new funding opportunities and developing sustainable financing strategies.
Documenting and sharing project lessons, best practices, and research findings to inform future initiatives.
Influencing policy decisions and legislation to create an enabling environment for women's economic empowerment.
Building a network of organizations and stakeholders to amplify impact and leverage resources.

## Slide 32
Gradually transferring project responsibilities to local partners and communities, ensuring a smooth transition.
Establishing a system to track progress, assess impact, and make data-driven decisions.
Identifying opportunities to expand project reach and impact, replicating successful models and strategies.
Handover of resources that will guide stakeholders involved to ensure a smooth transfer such as human and infrastructural resources.
Establishment of clear communication with stakeholders to ensure continuous address of questions, concerns, issues om the project after the transfer emphasizing the benefits of the project continuation under local leadership and address concerns or questions from the community.
Facilitate the transfer of knowledge and best practices to stakeholders and share project documentation, lessons learned, and successful strategies to ensure continuity.
Integrate the Women's Voice and Leadership Nigeria project into existing programs and initiatives of the stakeholders

## Slide 33
Conclusion
The Women’s Voice and Leadership Nigeria project has been impactful in Cross River State, guided by stakeholder engagement, capacity building, and a strong policy framework, have ensured the continued success of women economic empowerment, women's political participation and prevention of gender based violence against women and girls in the State.
Investing in capacity building, policy enhancement, community engagement, and monitoring mechanisms are needed to sustain the project. The winding down of the WVL project is not an end to itself but a transition to a new phase of major impact. By prioritizing this initiative, Cross River State can continue to empower women, promote gender equality, and foster a more inclusive political landscape. The sustainability of the project will contribute to the long-term development and empowerment of women in Cross River State.

## Slide 34
Appendices

## Slide 36
Acknowledgement:
We express our sincere gratitude to the donors of the WVL-Nigeria project, Global Affairs Canada (GAC). The implementation of interventions with the grant from the WVL-Nigeria project has indeed contributed towards the enjoyment of Women and Girls and the advancement of Gender Equality in Nigeria at different degrees and among a range of diverse populations even beyond the project’s focal states. Thank you.
We acknowledge and appreciate the leadership and guidance of the ActionAid Nigeria team throughout the past 5 years. Nkechi Ilochi-Kanny former ActionAid Women’s Rights Programme Manager/WVL-Nigeria Project Manager and current Director, Resource Mobilization and Innovation Directorate who started this journey with us and laid a solid foundation for us all. Niri Goyit the current Women’s Rights Programme Manager and manger of the WVL-Nigeria project who built a firm structure on the foundation laid by her predecessor deepening and consolidating on the gains. Vivian Efem-Bassey, the Manager Projects & Lagos office who also coordinates WVL partners in the Southern region, her consistent wide range of capacity building efforts, technical and moral support has contributed immensely in shaping us to the credible, effective and sustainable organizations that we are today.

## Slide 37
The entire WVL-Nigeria team ranging from those in Programmes, Communications, Finance, Monitoring, Evaluation and Learning, including the Senior Management Team of ActionAid Nigeria, your efforts are acknowledged and appreciated.
We also extend our sincere appreciation to the Government of Cross River State, Local Governments of Cross River State, the Ministry of Women Affairs, various stakeholders including traditional and religious leaders, civil society organisations, political parties, State Actors and community leaders etc., for their cooperation and support throughout the project. Their involvement was crucial in implementing policies and creating an enabling environment for women. Their commitment and collaboration have laid a strong foundation for sustained progress in women's empowerment and gender equality.
Thank you all for your dedication and support in making the Women's Voice and Leadership Nigeria project in Cross River State a success.

## Slide 38
THANK YOU!
SOSONG OOO!